## Executive Summary
EXECUTIVE OPERATIONS DASHBOARD
Doris Leslie Blau ¦ Monthly Operations Review ¦ Prepared by: Kachi Okonkwo
KEY PERFORMANCE INDICATORS — Current Period Snapshot
KPI | Owner | Target | Actual | vs. Target | Status | Trend | Notes
Projects On-Time Delivery Rate | Kachi Okonkwo | 0.9 | 92% | ✓ On Target | Green | ↑ | Source: Project tracker, this period
Budget Variance (All Active Projects) | Kachi Okonkwo | 0.05 | 3% | ✓ On Target | Green | → | Source: Finance reconciliation
Vendor SLA Adherence (Avg) | Kachi Okonkwo | 95% | 96% | ✓ On Target | Green | ↑ | Source: Vendor scorecard
Customs Delay Rate | Kachi Okonkwo | 2% | 1.5% | ✓ On Target | Green | ↓ | Source: Logistics data
Open Risk Items (High Priority) | Kachi Okonkwo | 0% | 0 | ✓ Clear | Green | → | Source: Risk register
Reporting Streams Consolidated | Kachi Okonkwo | 500% | 5 | ✓ Complete | Green | ↑ | Source: Dashboard log
BUDGET SUMMARY — Active Projects
Project | Budget Owner | Approved Budget ($) | Spent to Date ($) | Committed ($) | Remaining ($) | % Used | Variance ($) | Status
Logistics Optimization | Kachi Okonkwo | 250000 | 198000 | 22000 | 30000 | 79.2% | 30000 | On Track
Executive Reporting Infrastructure | Kachi Okonkwo | 85000 | 71000 | 8000 | 6000 | 83.53% | 6000 | On Track
Cross-Regional Project Q1 | Kachi Okonkwo | 420000 | 312000 | 65000 | 43000 | 74.29% | 43000 | On Track
Vendor Onboarding Program | Kachi Okonkwo | 95000 | 52000 | 18000 | 25000 | 54.74% | 25000 | On Track
Process Redesign Initiative | Kachi Okonkwo | 175000 | 88000 | 32000 | 55000 | 50.29% | 55000 | On Track
TOTAL |  | 1025000 | 721000 | 145000 | 159000 | 70.34% | 159000

## Risk Register
RISK REGISTER
Doris Leslie Blau ¦ Active Risk Tracking ¦ Prepared by: Kachi Okonkwo
ID | Risk Description | Category | Likelihood (1-5) | Impact (1-5) | Risk Score | Owner | Mitigation Action | Status
R-001 | Vendor SLA breach on key route during peak season | Logistics | 3 | 4 | 12 | Kachi Okonkwo | Pre-negotiate backup vendor; add clause to SLA agreements | Mitigating
R-002 | Budget overrun on cross-regional project due to scope creep | Financial | 3 | 5 | 15 | Kachi Okonkwo | Weekly variance reporting; change control process in place | Monitoring
R-003 | Customs regulation change in European markets | Compliance | 2 | 4 | 8 | Kachi Okonkwo | Monthly regulatory check; legal review of active shipments | Monitoring
R-004 | Key stakeholder unavailability causing decision delays | Execution | 4 | 3 | 12 | Kachi Okonkwo | Decision authority matrix; backup approvers defined per project | Mitigating
R-005 | Project timeline slippage due to vendor delay | Logistics | 3 | 3 | 9 | Kachi Okonkwo | Buffer built into roadmap; vendor escalation path documented | Mitigating
R-006 | Reporting data inconsistency across departments | Operational | 2 | 3 | 6 | Kachi Okonkwo | Single source of truth dashboard; data validation checks weekly | Resolved
R-007 | FX rate impact on international logistics costs | Financial | 2 | 4 | 8 | Kachi Okonkwo | Quarterly FX review with finance; spot hedging where applicable | Monitoring