## RACI Matrix
PROJECT GOVERNANCE: RACI MATRIX
Doris Leslie Blau ¦ Cross-Regional Project Delivery ¦ Prepared by: Kachi Okonkwo
LEGEND: R = Responsible (does the work) A = Accountable (owns the outcome) C = Consulted (provides input) I = Informed (kept in the loop)
# | Project Activity / Task | Phase | Project Manager (Kachi) | C-Suite Exec | Finance Lead | Ops Team | Vendor Partners | Legal / Compliance | External Stakeholders
1 | Define project scope and objectives | Initiation | A | C | C | C | I | I | I
2 | Stakeholder identification and mapping | Initiation | R | A | I | C | I | C | I
3 | Develop project roadmap and timeline | Planning | R | A | C | C | I | I | I
4 | Build and maintain risk register | Planning | R | A | C | C | I | C | I
5 | Budget planning and allocation | Planning | R | A | R | C | I | I | I
6 | Vendor contract negotiation | Planning | R | A | C | I | C | R | I
7 | Kick-off and alignment meeting | Planning | R | A | C | R | C | I | C
8 | Sprint cadence setup and facilitation | Execution | R | I | I | C | I | I | I
9 | Track milestones against roadmap | Execution | R | I | I | C | I | I | I
10 | Issue escalation and resolution | Execution | R | A | C | C | C | C | I
11 | Vendor performance monitoring | Execution | R | I | C | C | A | I | I
12 | Weekly status reporting to leadership | Execution | R | I | C | I | I | I | I
13 | Budget tracking and variance reporting | Execution | R | A | R | I | I | I | I
14 | Scope change assessment | Execution | R | A | C | C | C | C | I
15 | Stakeholder communications | Execution | R | A | I | C | C | I | C
16 | Final deliverable review | Closure | R | A | C | C | C | C | I
17 | Post-project retrospective | Closure | R | A | C | R | I | I | I
18 | Lessons learned documentation | Closure | R | A | C | C | I | I | I
RESPONSIBILITY SUMMARY
Each project activity has exactly one Accountable (A) owner. All ambiguity in ownership is resolved before execution begins.